## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Home page | 2024-12-16 | 2025-01-01 | 100% | Thư Võ | 2025-01-05 | 2025-01-05 | 100% | Thư Võ | The interface is similar to the model
List page | 2024-12-23 | 2024-01-02 | 100% | Thư Võ | 2025-01-05 | 2025-01-05 | 100% | Thư Võ | Full product categories when searching for keywords
Detail product page | 2025-12-24 | 2024-01-03 | 100% | Thư Võ | 2025-01-05 | 2025-01-05 | 100% | Thư Võ | Enough product information
Sign In page | 2025-12-15 | 2024-12-15 | 100% | Thư Võ | 2025-01-05 | 2025-01-05 | 100% | Thư Võ | Enough input to sign in
SignUp page | 2025-12-15 | 2025-12-15 | 100% | Thư Võ | 2025-01-05 | 2025-01-05 | 100% | Thư Võ | Enough input to sign in
Admin page | 2025-12-21 | 2025-12-29 | 100% | Trịnh Thành | 2025-01-07 | 2025-01-07 | 100% | Trịnh Thành | Enough input data
Admin Login page | 2025-12-21 | 2025-12-29 | 100% | Trịnh Thành | 2025-01-07 | 2025-01-07 | 100% | Trịnh Thành | Allows admin to manage all data
API task | 2024-12-16 | 2024-12-02 | 100% | Trịnh Thành, Thư Võ | 2025-01-07 | 2025-01-07 | 100% | Trịnh Thành, Thư Võ | All called APIs are available
API task update | 2024-12-16 | 2024-12-02 | 100% | Trịnh Thành | 2025-01-07 | 2025-01-07 | 100% | Trịnh Thành | No error occurred when updating API data